## Solution Options
Option | Description | Rough Order of Magnitude (ROM) Costs per annum
1 | Commercial Off the Shelf (COTS) Support provided by manufacturer | Total :$100K
2 | Open Source solution Installed and supported by Internal IT Department Community support for escalations | Specialist Resource to install and maintain: $30K IT Dept helpdesk 2*FTE: $40k Hardware cost: $20k Total: $90k
3 | In House solution created by a student supported by the developer and Internal IT Department | Developer $40k IT Dept helpdesk 2*FTE $40k Hardware cost $20k Total $100k

## Risk
Option 1
Ref | Risk Description | Consequence | Mitigation | P | I
R1 | Stable Internet connection required at all times | unable to access ERP platform | Dual internet pipes | low | severe
Option2
Ref | Risk Description | Consequence | Mitigation | P | I
R1 | No ability to flex with demand | will not be able to meet busiess flexibility | extra cost for more equipment | High | Severe
R2 | Duplicate hardware required to provide a basic level of resilience and redundancy | Extra cost | none | High | Severe
R3 | RPO and RTO timeframes are subject to hardware and staff abilities and cannot guarantee to meet the business needs | Does not meet business requirements | None | High | Severe
R4 | Resilience and redundancy is within a single site | single point of failure | None | High | Severe
R5 | No SLA of KPI for community support |  | None | High | Severe
Option3
Ref | Risk Description | Consequence | Mitigation | P | I
R1 | No ability to flex with demand | will not be able to meet busiess flexibility | extra cost for more equipment | High | Severe
R2 | Duplicate hardware required to provide a basic level of resilience and redundancy | Extra cost | none | High | Severe
R3 | RPO and RTO timeframes are subject to hardware and staff abilities and cannot guarantee to meet the business needs | Does not meet business requirements | None | High | Severe
R4 | Resilience and redundancy is within a single site | single point of failure | None | High | Severe
R5 | No SLA of KPI for developer or internal IT Dept support | will not be able to meet busiess flexibility | None | High | Severe
R5 | Student creator no longer part of the company | No further design available | employ student | HIgh | Medium

## Assumptions
Option 1
Ref | Assumption | Consequence If False | Date Cleared
A1 | Ability to provide RPO of 15 mins and RTO of 4 hrs
A2 | Current skills in place to provide support for solution
A3 | Agreed SLA and KPI with supplier
A4 | Train the trainer as part of the onboardig process
A5
Option 2
Ref | Assumption | Consequence If False | Date Cleared
A1 | Additional hardware and personnel to provide a business continuity plan but still unable to meet RPO of 15 mins and RTO of 4 Hrs
A2 | Additional training for OSS software
A3 | No SLA or KPI so impact to business upon incidents
Option 3
Ref | Assumption | Consequence If False | Date Cleared
A1 | Additional hardware and personnel to provide a business continuity plan but still unable to meet RPO of 15 mins and RTO of 4 Hrs
A2 | Additional training for in house software
A3 | No SLA or KPI so impact to business upon incidents

## Issues
Option 1
Ref | Issue Description | Date Cleared
I1 | Non identified at this point
Option 2 and 3
Ref | Issue Description | Date Cleared
I1 | Secure internal access solution would need to be created for external users
I2 | Need to learn the solution and how to deploy and support for 150 users
I3 | Staff leave and all gained knowledge and experience is lost

## Dependancies
Option 1
Ref | Dependency Description | Project
DP1 | Internet access | non project
DP2 | Continueing contract with provider | Onoing
Option 2 and 3
Ref | Dependency Description | Project
DP1 | IT dept for all support | non project
DP2 | Internal Helpdesk for all call resolutions
DP3 | Developer being retained by ACME